## Sheet1
ID Sev Pri OS Assignee Status Resolution Title
1376 [SEC] Cri to_ Andr bhargavix.h.kuligod@intel.com RESO DUPL TASKFORCE: Fabric error occurs while booting the system
1463 [SEC] Cri to_ Andr hitesh.k.patel@intel.com NEW System hang will happen when pressing power button and texture streaming for camera preview.
1467 [SEC] Cri to_ Andr fabricex.sorel@intel.com NEW Modem 6260 PnP issue and pending materials
1454 [SEC] Hig to_ Andr haijun.cao@intel.com NEW LIS3LV02DX accelerometer (I2C) driver is blocking during a voice call.
1449 [SEC] Hig to_ Andr rajeev.d.muralidhar@intel.com RESO DUPL System Sleep & Wake USB
1461 [SEC] Hig to_ Andr niveditha.sundaram@intel.com NEW MidCrypto deadlocks during concurrent operation
1455 [SEC] Hig to_ Andr hong.liu@intel.com NEW The proximity sensor driver blocks the s0i3
1282 [SEC] Hig to_ Andr zhengliex.song@intel.com RESO DUPL System die when playing video
1442 [SEC] Hig to_ Andr ramesh.agarwal@intel.com NEW Charging status inconsistent in WW17 Medfield Android Release
1453 [SEC] Hig to_ Andr howard.s.hamilton@intel.com NEW [PnP] Gfx not entering D0i3 during camera application workloads
1464 [SEC] Med to_ Andr bin.yang@intel.com NEW random S3 suspend panic in i2c_dw_xfer_msg for dev->msgs is NULL
1459 [SEC] Med to_ Andr erwanx.mahe@intel.com ASSI build_all: format errors in log output
1288 [SEC] Med to_ Andr sebastienx.niciarz@intel.com RESO DUPL L2CAP throuput test_uplink (CDK as Client) is failed.(the current average value is about 0.88Mb/s)
1458 [SEC] Med to_ Andr bruce.j.beare@intel.com ASSI Reboot after installer completes
1469 [SEC] Med to_ Andr christophex.lebouc@intel.com NEW SST timeout or GPADC timeout case caused phone hang after using vBB0.03 firmware
1290 [SEC] Med to_ Andr jeanx.trivelly@intel.com ASSI DUT can not iteratively switch connection from AP unsecured to AP secured 50 times.
1420 [SEC] Med to_ Andr rajeev.d.muralidhar@intel.com NEW s0ix support while some cpu offline
1460 [SEC] Med to_ Andr erwanx.mahe@intel.com ASSI troubleshoot.sh script is incorrect for gingerbread
1364 [SEC] Med to_ Andr gangx.a.chen@intel.com ASSI Power optimization: ALSA HAL setHardwareParams buffer changes for Music use-case
1448 [SEC] Med to_ Andr fabricex.sorel@intel.com NEW Modem power consumption is High in system Standby
1365 [SEC] Med to_ Andr panneer.s.arumugam@intel.com ASSI Power optimization: Optimize Audiotrack obtainBuffer wake-ups for Music use case
1382 [SEC] Med to_ Andr hongyu.zhang@intel.com RESO WONT Switching camera app from still to video switches ISP to video mode
1323 [SEC] Med to_ Andr eric.morel@intel.com NEED RF performance-modem : ACLR FDDII fails Intel specs
1446 [SEC] Med to_ Andr jack.ren@intel.com RESO DUPL [PnP] Observed high wakes during S0i3 when we set governor policy to Ondemand
1444 [SEC] Med to_ Andr xiaolin.zhang@intel.com RESO FIXE added 1080p and 720p capture resolution item support.
1423 [SEC] Med to_ Andr frederic.predon@intel.com RESO FIXE Revert the patches which break the telephony test 2011-04-26
1439 [SEC] Med to_ Andr haijun.cao@intel.com NEW High i2c-dw-pci-5 interrupts (60/s) from accelerometer sensor while playing video
1330 [SEC] Med to_ Andr erwanx.mahe@intel.com NEW No gerrit entry but filing a bug on gerrit slowness on viewing files
1468 [SEC] Med to_ Andr chao.bi@intel.com ASSI Fail to Import SIM phonebook to Device Phone Book
1413 [SEC] Med to_ Andr johnson.z.wu@intel.com RESO FIXE Audio record: Audio HAL should open alsa device with 44.1KHz as sampling rate
1438 [SEC] Med to_ Andr jian.a.zhu@intel.com ASSI iCDK can't camp on 2G live network in China
1371 [SEC] Med to_ Andr gangx.a.chen@intel.com RESO FIXE Keep the wired headset inserting into the board, the sound outputs from speaker &wired headset instead of only wired headset after playing the ringtone of "settings".
1443 [SEC] Med to_ Andr ramesh.agarwal@intel.com NEW Battery sysfs 'Charge_counter' starts with a negative value in WW17 Medfield Android Release
1373 [SEC] Med to_ Andr livingston.tong@intel.com NEW Could not download image onto one defect iCDK baseboard
1441 [SEC] Low to_ Andr lakshmi.n.vinnakota@intel.com RESO INVA Capture of Big Endian format files is failing
1333 [SEC] Low to_ Andr james.p.freyensee@intel.com NEW Please fix FW so we can reboot iCDK w/leaving USB plugged in
1419 [SEC] Low to_ Andr rajeev.d.muralidhar@intel.com NEW added weak platform_pm callbacks
1436 [SEC] Low to_ Andr saadi.maalem@intel.com NEW system crash when launch phone application (1/20)
1437 [SEC] Low to_ Andr saadi.maalem@intel.com NEW System freeze when setting normal ringtone (1/20)
1440 [SEC] Low to_ Andr lakshmi.n.vinnakota@intel.com RESO INVA Capture of 8 bit audio file is failing
1374 [SEC] Low to_ Andr shengquan.yuan@intel.com RESO FIXE mfld video driver codying style cleanup
1405 [SEC] Blo to_ Andr louis.le.gall@intel.com NEW Integration of alsa IFX sound card
1452 [SEC] enh to_ Andr nicolas.roux@intel.com ASSI [METABUG_KPI_PnP]
1307 [SEC] enh to_ Andr davidx.muoio@intel.com NEW Add support for POLLHUP on ttyIFX0
1398 [SEC] enh to_ Andr wen.w.wang@intel.com ASSI Need to update ISP driver for PNW C0 stepping
1415 [SEC] enh to_ Andr fabricex.sorel@intel.com RESO FIXE Update IFX FW to SUNRISE_SMB_1116.C
1407 [SEC] enh to_ Andr juliex.regairaz@intel.com NEW [NLCP] RSSI level is displayed as low
1414 [SEC] enh to_ Andr juliex.regairaz@intel.com NEW [NLCP] can't connect / disconnect to an AP twice
1403 [SEC] enh to_ Andr honorex.tricot@intel.com ASSI [NLCP] Wrong "Link Speed" for connected AP
1386 [SEC] enh to_ Andr jurgen.von.oerthel@intel.com NEW enable memory bandwidth read and write counters in the ISP firmware
1410 [SEC] enh to_ Andr juliex.regairaz@intel.com NEW [NLCP] No more scan after AP disconnection
1342 [SEC] enh to_ Andr jean-michelx.bachot@intel.com INTE FIXE Add WIDI Flag in Android build Makefile
1335 [SEC] enh to_ Andr jackx.w.lix@intel.com NEW Rapid RIL 5.5 Integration
1456 [SEC] enh to_ Andr jing.tao@intel.com ASSI atomisp driver contains hex constants
1295 [SEC] enh to_ Andr jeanx.trivelly@intel.com ASSI WLAN: Enabling WLAN Tethering
1383 [SEC] enh to_ Andr gang.a.hu@intel.com NEW libmfldadvci API exposes too much detail
1297 [SEC] enh to_ Andr juliex.regairaz@intel.com NEW WLAN: Scan time enhancements
1404 [SEC] enh to_ Andr juliex.regairaz@intel.com NEW [NLCP] Wifi state goes to unsuccessful state after sleep
1412 [SEC] enh to_ Andr juliex.regairaz@intel.com NEW [NLCP] Can't enable/disable WiFi twice
479 [SEC] Cri P1 Andr randy.xu@intel.com ASSI [Video]: System is easy to hang when Gfx PVR_K timeout is found during video playback
800 [SEC] Cri P1 Andr jackx.w.lix@intel.com RESO FIXE WIFI activation failed
500 [SEC] Cri P1 Andr yan.a.wang@intel.com RESO FIXE boot from eMMC (with kernel+rootFS) is not stable in some board
745 [SEC] Cri P1 Andr timothy.c.dietz@intel.com RESO FIXE S0i3 not working on IFWI B0.14
941 Cri P1 Andr jenny.tc@intel.com ASSI PnP: PnP iCDK board unstable for S0i3 measurements compared to iCDK boards
1339 [SEC] Cri P1 Andr saadi.maalem@intel.com NEW Puint FW shut down Iunit power before driver has finished context save which will cause system hang
1304 [SEC] Cri P1 Andr yang.chang@borqs.com ASSI Apps manager does not release memory as it should
608 [SEC] Cri P1 Andr livingston.tong@intel.com RESO FIXE PR1 Display very dim or black
1001 Cri P1 Andr eduardox.mendi@intel.com INTE FIXE [PnP] USB B cable unplug is not recognised correctly with latest USB runtime_pm patches
1302 [SEC] Cri P1 Andr loicx.martin@intel.com INTE FIXE SPI debug uart does not work after S3
439 [SEC] Cri P1 Andr eric.seibel@intel.com RESO FIXE platform failed to camp on network - modem not camp
1052 Cri P1 Andr christophex.lebouc@intel.com RESO DUPL mdfld-Android - Frequent Fabric Error Occerance(F503) in Medfield iCDK Boards
607 [SEC] Cri P1 Andr christophex.lebouc@intel.com ASSI PNP:Random Fabric Errors observed while booting Android builds
1281 [SEC] Cri P1 Andr rakesh.a.ughreja@intel.com ASSI Board die when play audio
1252 [SEC] Cri P1 Andr philippe.skowronski@intel.com ASSI SIM status is UNKNOWN
718 [SEC] Cri P1 Andr jing.tao@intel.com RESO FIXE go to s0i3 while preview will cause system hang
600 [SEC] Cri P1 Andr olivier.carpentier@intel.com RESO FIXE BKB MFD PR1 (aka BB2) board temperature is too hot]
837 [SEC] Hig P1 Andr xiaolin.zhang@intel.com RESO FIXE System hang when call QBUF v4L2 IOCTL with a wrong buffer index.
694 [SEC] Hig P1 Andr frederic.predon@intel.com ASSI Boot failures 1/5
1213 Hig P1 Andr jurgen.von.oerthel@intel.com ASSI 1080p video recording will have green blocks at the center of the viewfinder
1408 [SEC] Hig P1 Andr eric.morel@intel.com NEW RF perf/modem : modem reboot / Pmax WCDMA
692 [SEC] Hig P1 Andr jackx.w.lix@intel.com RESO FIXE Rapid RIL is not correctly synchronized with STK application
546 [SEC] Hig P1 Andr ping.liang@intel.com INTE FIXE [Audio] one audio clip in mp4 file container with mp3 codec makes music player crash
535 [SEC] Hig P1 Andr celinex.chotard@intel.com RESO FIXE [Video]obtainBuffer timed out error happens and video playback only shows a still frame (40% reproducibility)
715 [SEC] Hig P1 Andr thierry.deleau@intel.com RESO FIXE Include AT proxy project and checkin code
1276 [SEC] Hig P1 Andr christophex.lebouc@intel.com INTE FIXE Temporary UI freeze with IFW BE.15
791 [SEC] Hig P1 Andr jing.tao@intel.com ASSI [PnP] ISP (Camera Imaging IP) is not power gated in S0 Idle mode
1094 Hig P1 Andr rajeev.d.muralidhar@intel.com RESO FIXE [Taskforce] SDHC causes fabric errors during S3 resume
1317 [SEC] Hig P1 Andr wei.gao@borqs.com RESO DUPL [Camera] Camera crashes when switching between front camera and back camera
794 [SEC] Hig P1 Andr johnson.z.wu@intel.com ASSI 0001606: [Music Player] Music can't resume after end a call
1350 [SEC] Hig P1 Andr hao.wu@intel.com RESO WORK [OSPM] Plug USB micro B when DUT in S0i3 makes it to reset
1137 Hig P1 Andr weian.chen@intel.com RESO FIXE The encoded clips have green frame and corruption in MFLD Android R4.3
1305 [SEC] Hig P1 Andr christophe.continente@intel... ASSI libc_malloc_debug_leak.so is not working
632 [SEC] Hig P1 Andr jason.m.bills@intel.com ASSI Android kernel can not be loaded when power up with usb cable plugged
1208 Hig P1 Andr li.zeng@intel.com RESO FIXE [PnP]Video playback stops working after 30sec and system does not respond after that
1159 Hig P1 Andr saadi.maalem@intel.com NEW Taskforce : Android mfld : Platform does not enter into S0i3/S3 using Punit Fix FW.
617 [SEC] Hig P1 Andr hassenex.ben.abdallah@intel... ASSI [AUDIO] Playback audio MP3 crash audio when moving cursor on progress bar
734 [SEC] Hig P1 Andr fabienx.barthes@intel.com RESO FIXE [Video] "ObtainBuffer timed out" error happens during plugging out earphone (40% re-producibility)
1080 Hig P1 Andr timothy.c.dietz@intel.com NEW LPE clock was changed to 200MHz during LPE clock switching for 1 usync period causing LPE stops execution
962 Hig P1 Andr arvind.s.tomar@intel.com ASSI I2S Pins Configuration in D0i3/S0i3
1409 [SEC] Hig P1 Andr jenny.tc@intel.com ASSI After more than 90mins of audio/video playback system is shutdown
ID Sev Pri OS Assignee Status Resolution Title
1381 [SEC] Hig P1 Andr mark.a.allyn@intel.com ASSI Spurious interrupts (irq 25) while entering S0i3
1153 Hig P1 Andr rajesh.poornachandran@intel... ASSI [PnP] Latest Android build Gfx driver down not handle display OFF case properly; display panel consumes 157mW
811 [SEC] Hig P1 Andr kun.k.wang@intel.com ASSI Memory leak cause video playback hang (without audio) after a long time
1389 [SEC] Hig P1 Andr rajesh.poornachandran@intel... ASSI call to new IPC command required to solve display panel overconsumption in display OFF
1298 [SEC] Hig P1 Andr timothy.c.dietz@intel.com ASSI DUT logs from PTI are often corrupted
1313 [SEC] Hig P1 Andr juliex.regairaz@intel.com REOP [WLAN]the connection with AP broke automatically after surfing internet for a while.
1097 Hig P1 Andr sundar.iyer@intel.com RESO FIXE [PNP] Set the default governor as ondemand instead of performance
1343 [SEC] Hig P1 Andr vgonzalez@intrinsyc.com ASSI Call Barring queries using MMI codes are failing
542 [SEC] Hig P1 Andr laura.l.warner@intel.com RESO WONT Screen frozen while browsing with the UI
924 Hig P1 Andr xiaolin.zhang@intel.com RESO WORK Viewfinder freezes after selecting any of the Color Effects.
1380 [SEC] Hig P1 Andr jayant.mangalampalli@intel.com ASSI MidCrypto DH param stresses begin failing, DUT reboots
482 [SEC] Hig P1 Andr xiaowei.a.li@intel.com RESO FIXE [Video]Fail to play some H.263 Video clips
1219 Hig P1 Andr erwanx.mahe@intel.com ASSI Watchdog daemon absent from test cycle build
1145 Hig P1 Andr rose.w.han@intel.com RESO FIXE Mfld/Android: v-sync switch not included in build (R4.3)
1277 [SEC] Hig P1 Andr leo.he@borqs.com INTE FIXE libdl.so.2 missed in device/intel/kboot/in/initrd-base.gz
1076 Hig P1 Andr nicolas.roux@intel.com NEW MFLD_Android:-PMU Driver functionality is not enabled(S3 and S0i3)
1264 [SEC] Hig P1 Andr rajeev.d.muralidhar@intel.com REOP Panics when press power button while camera previewing
1430 [SEC] Hig P1 Andr erwanx.mahe@intel.com ASSI Merge of both mfld_cdk and mfld_pr1 folder
1266 [SEC] Hig P1 Andr johnson.z.wu@intel.com RESO FIXE Can't detect wired headset when insert the wired headset before booting up the board
993 Hig P1 Andr li.zeng@intel.com RESO DUPL error message is printed during video playback error
984 Hig P1 Andr tim.coppernoll@intel.com RESO FIXE Chaabi verification of a signed OS fails during normal boot, but not DnX
1327 [SEC] Hig P1 Andr chuanxiao.dong@intel.com RESO FIXE [SD/MMC]there is a race between card-detect rescan and clock-gate work instances
1378 [SEC] Hig P1 Andr hao.wu@intel.com RESO DUPL USB suspend fix for S3
932 Hig P1 Andr alek.du@intel.com ASSI Taskforce: Mtfld-Android No Driver with D3/D0i3 for UART0
914 Hig P1 Andr gang.a.hu@intel.com RESO FIXE Video Recording - selecting a recording quality other than High (Low, MMS, Youtube) crashes the camera app.
1038 Hig P1 Andr jason.m.bills@intel.com ASSI Can't charge battery more than 3.4V if power button is enabled
1172 Hig P1 Andr liang.l.yang@intel.com RESO FIXE System hang when switch capture mode to video recording mode with OV2720 camera.
1417 [SEC] Hig P1 Andr saadi.maalem@intel.com NEW Phone goes in sleep mode after releasing a Voice call
830 [SEC] Hig P1 Andr yanmin.zhang@intel.com RESO DUPL Video cannot be played by s0i3[PmP]
1293 [SEC] Hig P1 Andr jason.m.bills@intel.com RESO FIXE Playback audio regression
1154 Hig P1 Andr rajesh.poornachandran@intel... ASSI [PnP] Pipe C should be OFF if any one MIPI panel is attached
714 Hig P1 Andr suhail.ahmed@intel.com ASSI Modem FW 1112_pre2 breakes HSI communication with Coriolis SIM card
1258 [SEC] Hig P1 Andr wen.w.wang@intel.com ASSI Random kernel hang observed while booting Android builds
1275 [SEC] Hig P1 Andr juliex.regairaz@intel.com RESO FIXE [PnP]UDP Downlink is terminating the Wi-Fi connection in ELP Mode.
383 [SEC] Hig P1 Andr livingston.tong@intel.com RESO FIXE Can't capture image from the primary camera
1303 [SEC] Hig P1 Andr timothy.c.dietz@intel.com NEW PTI does not work after S0i3 or S3
613 [SEC] Hig P1 Andr yong.yao@intel.com RESO DUPL [Audio] There is no sound via the wired headset when play a music
1384 [SEC] Hig P1 Andr davidx.muoio@intel.com NEW The modem often does not respond after resetting it.
1226 [SEC] Hig P1 Andr suhail.ahmed@intel.com ASSI HSI driver does not support runtime power management
849 [SEC] Hig P1 Andr aymenx.zayet@intel.com ASSI [PnP] Unable to enter in S0i3 mode during voice call
1400 [SEC] Hig P1 Andr lakshmi.n.vinnakota@intel.com ASSI audio fail after resume from s3
1357 [SEC] Hig P1 Andr suhail.ahmed@intel.com RESO INVA SUNFISE_SMB_1110.01 cannot be downloaded via HSI port
1349 [SEC] Hig P1 Andr gilles.rimauro@intel.com RESO DUPL [OSPM] Voice call does not wake up device from S0i3 and phone call no more possible when system is woken up from S0i3
687 [SEC] Hig P1 Andr dong.yang@intel.com RESO FIXE fatal signal 11 in WebViewCoreThre cause browser crash.
1421 [SEC] Hig P1 Andr livingston.tong@intel.com ASSI MSIC : Headset detection is not consistent in MFLD PR1 board
1051 Hig P1 Andr sebastienx.niciarz@intel.com RESO FIXE mdfld-Android Shared Transport Driver Not Enabled (BT, FM, GPS)
829 [SEC] Hig P1 Andr vijay.bhimarao@intel.com ASSI Don't wake up from s0i3[PmP]
1388 [SEC] Hig P1 Andr bin.yang@intel.com RESO FIXE new command required to solve display panel overconsumption in display OFF
486 [SEC] Hig P1 Andr selina.wang@intel.com RESO FIXE [Camera] Camera crashes with dark screen after changing the video recording quality from high to low, and also crash after changing between front camera and back camera
875 Hig P1 Andr christophex.lebouc@intel.com RESO DUPL XML Workaround for Bug 3149160 - 20k PD on SDIO_WP pin is not reliable
623 [SEC] Hig P1 Andr eric.seibel@intel.com RESO FIXE Power key not working: not able to switch off the phone
1355 [SEC] Hig P1 Andr pranav.k.sanghadia@intel.com NEED gsmttys are created but RIL does not create network interface and no signal bars
588 [SEC] Hig P1 Andr johnson.z.wu@intel.com REOP PnP: Browser plugins(mp3, flash) not avialable on Android-Gingerbread build
827 [SEC] Hig P1 Andr li.zeng@intel.com RESO FIXE Video play will fail after s0i3.
1324 [SEC] Hig P1 Andr thomasx.guillemin@intel.com REOP Android phone Application crashes
1301 [SEC] Hig P1 Andr hao.wu@intel.com RESO FIXE USB does not work after S3
1375 [SEC] Hig P1 Andr rajeev.d.muralidhar@intel.com NEW TASKFORCE: 'Ack_C6 Timeout' print appear on SCU terminal when device in S0i3 on build WW18.1
1129 Hig P1 Andr weian.chen@intel.com RESO FIXE Video corruption occur when playing this parkrun mp4 clip
1450 [SEC] Hig P1 Andr erwanx.mahe@intel.com NEW Build: PR2 Specific projects needs to be created
1411 [SEC] Hig P1 Andr chuanxiao.dong@intel.com ASSI MMC causes fabric error during long hour audio playback
555 [SEC] Hig P1 Andr alainx.kouassu@intel.com RESO FIXE Inter RAT cell reselection 3G to/from 2G fails (iCDK ES2)
1424 [SEC] Hig P1 Andr hao.wu@intel.com ASSI System hangs after exiting from s3 if plugging in USB cable when system sleeps at s3
1175 Hig P1 Andr weian.chen@intel.com RESO FIXE SPS/PPS stripping in AVC encoder omx component causes distortion with non-MPEG4 output
710 [SEC] Hig P1 Andr fabienx.barthes@intel.com RESO FIXE [PnP] Audio init issue, high power consumption in IDLE (VIHFVIN)
950 Hig P1 Andr timothy.c.dietz@intel.com NEW Failed to get USB wake ups interrupts from MSIC, when USB is in D0i3 state.
1205 Hig P1 Andr yaney.rodriguez@intel.com REOP Battery sysfs and charger sysfs are not getting updated on removing USB OTG Charger.
1107 Hig P1 Andr jason.m.bills@intel.com ASSI MFLD_Android: Camera Button as a wake source does not wake the system from S0i3 state
1354 [SEC] Hig P1 Andr niveditha.sundaram@intel.com NEW IRQ25 disable after a period of inactivity
790 [SEC] Hig P1 Andr yannx.billet@intel.com REOP [PnP] GL3 (L3 Cache) is not Power Gated in Idle (S0) Display ON and OFF use case
1195 Hig P1 Andr rajesh.poornachandran@intel... NEW [PnP]Turn off DUAL MIPI Port by default
1209 Hig P1 Andr timothy.c.dietz@intel.com ASSI S0ix-1 and s0ix-2 will hang while exercising Power Management capabilities.
1321 [SEC] Hig P1 Andr timothy.c.dietz@intel.com ASSI Audio playback over MSIC regression with SCU FW B0.26
1182 Hig P1 Andr asit.kumar.verma@intel.com RESO FIXE PnP Android: TMD Display panel/touch screen power is more then 7 mW even for Display off case.
1065 Hig P1 Andr jayant.mangalampalli@intel.com ASSI CHAABI2SCU_UMIP_WRITE hangs systems when data size is given very large number (fuzzing)
913 Hig P1 Andr venkateswarlu.v.vinjamuri@i... RESO FIXE [PnP] 76 interrupts from pvrsrvkm driver on idle android/Medfiled system
532 [SEC] Hig P1 Andr sumod.cherukkate@intel.com ASSI 0001305: [Calling]Can not make a MO call via the key on the headset.
939 Med P1 Andr li.zeng@intel.com RESO DUPL [PnP]Dynamic support for overlay during video playback
883 Med P1 Andr jiebing.li@intel.com RESO FIXE PROMOTE from penwell: AVE_CV: USB BULK OUT endpoint STALL on USBTEST compliance test suite
658 [SEC] Med P1 Andr hao.wu@intel.com RESO WORK PROMOTE from penwell: AVE_CV: Android Fabric error when switching between USB Client, host and idle mode
622 [SEC] Med P1 Andr niveditha.sundaram@intel.com ASSI PROMOTE from penwell: PUnit security keys are not being sent after S0i2/S0i3
503 [SEC] Med P1 Andr hongyu.zhang@intel.com RESO FIXE [Camera] Image capture only supports 640x480 resolution 540KB file size
1022 Med P1 Andr jayant.mangalampalli@intel.com ASSI POS: secureIPC_ATP test app fails to run srtc read test
801 [SEC] Med P1 Andr yuanx.xu@intel.com RESO FIXE [Video]Playback H263, H264 and MPEG4-AAC videos formats are failed on PR1
1006 Med P1 Andr chuansheng.liu@intel.com RESO DUPL CWS WLAN: Cannot play Quicktime video due to there isn't the application for Android
1259 [SEC] Low P1 Andr hong.liu@intel.com INTE FIXE Random kernel hang observed while booting Android builds for bh1770glc_probe
1280 [SEC] enh P1 Andr laura.l.warner@intel.com ASSI [METABUG] Top Telephony Issues
587 [SEC] enh P1 Andr saadi.maalem@intel.com ASSI [METABUG] WSIV ST - TOP BZ
1308 [SEC] enh P1 Andr chuanxiao.dong@intel.com ASSI please add a partition on SD card.
589 [SEC] enh P1 Andr wen.w.wang@intel.com ASSI PnP:ISP subsystem is in D0 in Android builds(Weekly 0318)
840 [SEC] enh P1 Andr jian.feng.qin@intel.com NEW [METABUG] Platform Integration Top 10 Audio/Video/Camera/Graphics Defects
1402 [SEC] enh P1 Andr gangx.a.chen@intel.com RESO INVA TTY audio configuration is not handled
690 [SEC] enh P1 Andr christophex.lebouc@intel.com ASSI [METABUG] Boot instabilities
731 [SEC] enh P1 Andr saadi.maalem@intel.com NEW [METABUG] Platform Integration Top 10 Defects
1265 [SEC] enh P1 Andr laura.l.warner@intel.com NEW [METABUG] Platform CWS Integration Top 5 Defects
1347 [SEC] enh P1 Andr selma.bensaid@intel.com ASSI LPE registers concerning SSPs need to be modified for SSP I2S Driver
674 [SEC] enh P1 Andr tanx.v.le@intel.com REOP CWS WLAN: [Android] Video download hung up while playing back and FTP file transfer failed
1306 [SEC] enh P1 Andr saadi.maalem@intel.com NEW [METABUG] - Memory Leaks
1048 Cri P2 Andr frederic.predon@intel.com RESO FIXE mtfld-Android - High speed Interface not enabled (HSDPA Modem).
712 [SEC] Hig P2 Andr jim.stanley@intel.com RESO DUPL HSI driver stack requires PM, fix to TTY creation, reset/shutdown handling
1200 Hig P2 Andr loicx.martin@intel.com ASSI [PnP] long S0 periods during S0i3 on latest Androind build WW15 (0407)
ID Sev Pri OS Assignee Status Resolution Title
1130 Hig P2 Andr sebastienx.niciarz@intel.com RESO FIXE Can use the BT headset receive a call, but the voice cannot transferred by BT headset
430 [SEC] Hig P2 Andr jean-christophe.sinet@intel... ASSI PnP: Modem 2G/3G voice call ,high power consumption
591 [SEC] Hig P2 Andr jing.tao@intel.com REOP PnP:Video subsystem is in D0 in Android builds(Weekly 0318) in idle
1078 Hig P2 Andr randy.xu@intel.com RESO FIXE [PnP Android] Gfx driver Keep CPU busy during Idle Display ON (C0 residency 80%)
1024 Hig P2 Andr christophex.lebouc@intel.com RESO FIXE microSD card couldn't be detected when it was insertted after the sytem booted up.
1166 Hig P2 Andr erwanx.mahe@intel.com ASSI Stale software and IFWI components block multiple tests in test cycle releases
789 [SEC] Hig P2 Andr li.zeng@intel.com VERI FIXE Task Force:[PnP] D0i3 NOT functional (Regression) for VED/VEC IP's in latest driver package
1018 Hig P2 Andr yaney.rodriguez@intel.com RESO FIXE Battery : Coulomb counter to charge_now bad conversion
1063 Hig P2 Andr nicolas.roux@intel.com ASSI Taskforce: [PNP Android]: AVg VnnAON rail power for forced Soi3 is at 6 mW higher then meego @3mW,target is less then 1 mW.
429 [SEC] Hig P2 Andr karl.rielland@intel.com ASSI UI freeze after boot in home sceen
1351 [SEC] Hig P2 Andr erwanx.mahe@intel.com ASSI Releases later than 0419 do nt contain kernel modules anymore
992 Hig P2 Andr al.bettner@intel.com RESO DUPL CWS WLAN: Cannot configure browser settings for proxy server to connect to internet
947 Hig P2 Andr mark.a.allyn@intel.com NEED Graphics driver interferes with operation of sep device
1329 [SEC] Hig P2 Andr liang.sun@borqs.com ASSI Audio AMC is using incorrect modem DLC
711 [SEC] Hig P2 Andr yijin.sun@intel.com INTE FIXE [PnP] Audio driver issue, high power consumption in IDLE (VAUDAVIN)
713 [SEC] Hig P2 Andr suhail.ahmed@intel.com RESO FIXE /dev/ttyIFX might not be integrated properly on HSI Medfield Android R4.3
1101 Hig P2 Andr hong.liu@intel.com ASSI Taskforce: Touchscreen not resuming on resume from S3
610 [SEC] Hig P2 Andr nicholas.j.yoke@intel.com RESO FIXE Enabling NFC on iCDK and BlackBay through SFI Table
985 Hig P2 Andr olivier.carpentier@intel.com RESO FIXE Unable to browse media files stored in SD Card from user apps (Media Player/ Gallery)
1068 Hig P2 Andr sameerx.lattannavar@intel.com INTE FIXE TASK_FORCE: Running Audio post S0i3 hangs the system with iERR
1066 Hig P2 Andr asit.kumar.verma@intel.com NEED [PNP Android]: V_1P22_VCCAON_CSI avg power for forced S0i3 is @ 1.5 mW .Target is few microwatts.
987 Hig P2 Andr lakshmi.n.vinnakota@intel.com RESO WORK HSMIC capture is silent
963 Hig P2 Andr suhail.ahmed@intel.com ASSI There is a read error when a test app first tries to issue AT command to /dev/ttyIFX0 port
1055 Hig P2 Andr santhosh.k.reddy.s@intel.com ASSI MFLD_Android : Wakeups caused by Surfaceflinger and Activity manager are very high on WW11.5 Gingerbread build when the board is in S0i3.
685 [SEC] Hig P2 Andr vamsi.krishnax.guturu@intel... RESO INVA [PnP]Low UDP throughputs(Uplink & Downlink) in Wi-Fi
1422 [SEC] Hig P2 Andr jianli.zhang@borqs.com ASSI The browser automaticall quit/close after loading only one web page
1328 [SEC] Hig P2 Andr suhail.ahmed@intel.com NEW [PnP] Modem high power consumption (30mA) in IDLE with HSI IFWI
934 Hig P2 Andr fengwei.yin@intel.com ASSI {BKB2]When touch TS during 1st 8 sec of kernel boot stops TS and kybrd from functioning properly
1064 Hig P2 Andr gilles.rimauro@intel.com ASSI Taskforce: [PNP Android]:VCCPADXXXAON_1P20 avg power for forced S0i3 is @ 8 mW higher then 7.5 mW observed on meego builds and targets.
707 [SEC] Hig P2 Andr petrix.harri@intel.com RESO FIXE Wifi download transfer failed
729 [SEC] Hig P2 Andr sebastien.cayetanot@intel.com RESO FIXE No Audio on BT HFP headset when MO/MT call
920 Hig P2 Andr venkateswarlu.v.vinjamuri@i... NEW [pnp] ILB patch porting from Meego kernel to Android
744 [SEC] Hig P2 Andr dominique.grange@intel.com RESO DUPL Wrong battery temperature reading
1433 [SEC] Hig P2 Andr lakshmi.n.vinnakota@intel.com RESO DUPL alsa_arecord utility is crashing while recoding loud voice for dual channel by using DMIC.
1236 [SEC] Hig P2 Andr ramesh.babu@intel.com RESO WORK Call with a wired headset, the other side cannot hear the voice, I can hear the voice.
577 [SEC] Hig P2 Andr frederic.predon@intel.com RESO FIXE Release one active call by pressing ¡°1¡±+SEND doesn¡¯t work while second call on hold
1395 [SEC] Hig P2 Andr livingston.tong@intel.com ASSI Primary camera not displaying the proper direction of the image.
583 [SEC] Hig P2 Andr sebastienx.niciarz@intel.com ASSI [PnP]BT- Low uplink throughput(l2test)
1337 [SEC] Hig P2 Andr bin.yang@intel.com ASSI adc driver timeout when play video for a long time -- msic_adc msic_adc.16: sample timeout
906 Hig P2 Andr jim.stanley@intel.com RESO FIXE HSI with DMA: Pio timeout causing troubles (loss of messages) in dma mode
1083 [SEC] Hig P2 Andr guoqiang.cao@intel.com ASSI Mfld/Android/GB: GridMark failed
964 Hig P2 Andr philippe.skowronski@intel.com ASSI Running wget to downland a large compressed file over HSI stack tends to get the received file in a corrupted state
1222 Hig P2 Andr jurgen.von.oerthel@intel.com ASSI Digital Zoom running in ISP preview mode with RGB565 format has a green line in the top of the image.
788 [SEC] Hig P2 Andr pierre.tardy@intel.com ASSI Taskforce: [PNP Android]: AVg VnnAON rail power for forced Soi3 is at 6 mW higher then meego @3mW,target is less then 1 mW.
1272 [SEC] Hig P2 Andr selma.bensaid@intel.com ASSI Intel MID I2S: Remove temporary workaround patch [http://android.intel.com:8080/#change,5839]
797 [SEC] Hig P2 Andr jin.xiao@intel.com ASSI Signal bar lost during browsing
764 [SEC] Hig P2 Andr laurentx.fert@intel.com ASSI [Audio] System freeze when playing AMR NB audio file iterative
1394 [SEC] Hig P2 Andr xiaolin.zhang@intel.com ASSI Different resolution have different Field of View (FOV).
1010 Hig P2 Andr frederic.predon@intel.com RESO FIXE Unsollicited modem reset not handled properly
717 [SEC] Hig P2 Andr jing.tao@intel.com RESO FIXE camera take picture cause driver crash after s0i3
1121 Hig P2 Andr randy.xu@intel.com RESO FIXE [Android PnP] High CPU utilization by events/0 on GB0325 build in S0/Idle
1346 [SEC] Hig P2 Andr frederic.predon@intel.com ASSI FTP data connection drop during cell reselection 3G <-> 2G
747 [SEC] Hig P2 Andr haijun.cao@intel.com RESO WORK [PnP] HTML5 Video not playing in Android-Gingerbread
807 [SEC] Hig P2 Andr wei.gao@borqs.com ASSI [Audio] Audio file from rtsp server cannot be played via streaming player
1334 [SEC] Hig P2 Andr james.p.freyensee@intel.com NEW Need way to pause automated kboot to flash problem kernels
1023 Hig P2 Andr yaney.rodriguez@intel.com NEW Interrupts not getting generated for peak current control
1110 Hig P2 Andr christophex.lebouc@intel.com RESO FIXE New SFI Table entry for fuel gauge chip
1369 [SEC] Hig P2 Andr ke.ai@intel.com NEED flashing dot dash line appears at the right side of some full screen displayed images
1090 Hig P2 Andr ganeshx.petkar@intel.com RESO FIXE Noise heard from IHF randomly
523 [SEC] Hig P2 Andr alainx.kouassu@intel.com ASSI HSDPA Throughput is too low
526 [SEC] Hig P2 Andr juliex.regairaz@intel.com RESO FIXE CWS-WLAN: Features are not integrated or only partially integrated - cannot test
1245 [SEC] Hig P2 Andr nicolas.roux@intel.com RESO DUPL MDFLD_OSPM: System does not enter into LPMP3 state
888 Hig P2 Andr timothy.c.dietz@intel.com NEW AONT timer wake wakes up system from S3
1204 Hig P2 Andr yaney.rodriguez@intel.com NEW DTS driver not registered for MDFLD_ANDROID_WW15 Release.
1352 [SEC] Hig P2 Andr cyrillex.nivelle@intel.com ASSI [OSPM] Board crashed in S0i3 when receiving data from a WLAN Iperf
766 [SEC] Hig P2 Andr arnaud.devreese@intel.com ASSI WLAN : MAC provisionning secure partition
1194 Hig P2 Andr timothy.c.dietz@intel.com ASSI TASK FORCE: S0i1 is not happening on the first run after boot on WW15.5 and WW16.1. S0i1 does not happen and we see a SCU hang.
538 [SEC] Hig P2 Andr santhosh.k.reddy.s@intel.com ASSI PnP: WCDMA/3G PS Data connection lost very frequently
1428 [SEC] Hig P2 Andr jianli.zhang@borqs.com NEW when input the command in terminal emulator sometimes, the system reboot.
1312 [SEC] Hig P2 Andr nicholas.j.yoke@intel.com NEW Could not get the expected value(0x0a) from OSNIBR.RR for EM use case P_CAP_40107
1058 Hig P2 Andr fengwei.yin@intel.com RESO DUPL System get lots of interrupt lost error messages and SCU 7-led show F503
976 Hig P2 Andr jiebing.li@intel.com ASSI Charging current incorrect when DUT connect to Medfiled Host
1143 Hig P2 Andr jayant.mangalampalli@intel.com ASSI DSS Chip Tool installer does not build with Win7/VS2010 Pro
1152 Hig P2 Andr guoqiang.cao@intel.com ASSI [PnP] Gfx KPI - 3DMM ES2.0 Taiji/Hover targets not met
267 [SEC] Hig P2 Andr zhenjie.pan@intel.com RESO FIXE [Storage] DUT can not mount the SD card after format it
748 [SEC] Hig P2 Andr nicolas.petit@intel.com RESO FIXE Can not find libpn544_fw.so in current Gingerbread SW version
495 [SEC] Hig P2 Andr randy.xu@intel.com ASSI [video] playback of a few MP4 (H264/AVC) files fail with Erroneous page count. Leaking Pages
979 Hig P2 Andr christophex.lebouc@intel.com RESO FIXE System to go to AD / Charging OS until SMIP.IA_APPS_RUN threshold reached
1223 Hig P2 Andr jurgen.von.oerthel@intel.com ASSI Digital zoom running in ISP primay mode and video 1080p easy to cause ISP timeout
524 [SEC] Hig P2 Andr carlos.pargada@intel.com REOP HSUPA Throughput is too low
960 Hig P2 Andr sylvestrex.dischamp@intel.com ASSI Dialing state is not returned through XCALLSTAT for SIM Toolkit SETUP CALL command
1013 Hig P2 Andr nicolas.roux@intel.com NEW Medfield-Android: Device not able to enter LPMP3 when display is off and music is playing
1322 [SEC] Hig P2 Andr sylvestrex.dischamp@intel.com ASSI Modem hangs after 126 B2B MT Voice calls
1059 Hig P2 Andr christophex.lebouc@intel.com NEW KBOOT shouldn't be stored on the usr data area of eMMC card.
1025 Hig P2 Andr yaney.rodriguez@intel.com NEW Peak_Current_Control sysfs action_mask shows incorrect value
810 [SEC] Hig P2 Andr fredericx.berat@intel.com RESO FIXE Mobile Terminated SMS class 2 are not saved in SIM card
1300 [SEC] Hig P2 Andr christophe.continente@intel... RESO DUPL Tapping on touch screen does not wake the platform - 20110419-001 build with IFWI v0.15
1158 Hig P2 Andr tim.coppernoll@intel.com INTE FIXE Interrupts appear when playback is initiated on HS through alsa_aplay
1338 [SEC] Hig P2 Andr kerry.vander.kamp@intel.com ASSI After cold boot, IAFW boot COS or MOS randomly
1425 [SEC] Hig P2 Andr rajeev.d.muralidhar@intel.com ASSI kernel panic during s3 stress testing
1289 [SEC] Hig P2 Andr nicolas.roux@intel.com RESO FIXE MDFLD_OSPM:Long hour S0i3 test fails
1432 [SEC] Hig P2 Andr saadi.maalem@intel.com NEW ULFM activation causes UI/kernel freezes
813 [SEC] Hig P2 Andr heng.su@intel.com NEW platfrom can not boot up from sd card
1206 Hig P2 Andr jenny.tc@intel.com NEW Battery charge_control register shows incorrect value
1027 Hig P2 Andr christophe.guerard@intel.com ASSI POS: chaabi2scu_mip_read hangs
1019 Hig P2 Andr sameerx.lattannavar@intel.com RESO FIXE Taskforce: MFLD_Android : Display does not turn on after GFX transitioning from D3 to D0
716 [SEC] Hig P2 Andr davidx.muoio@intel.com RESO FIXE Unable to communicate with modem through TTY interface /dev/ttyIFX0
927 Hig P2 Andr asit.kumar.verma@intel.com NEW [PnP] High S0 activity during exits from S0i3 increasing power consumption on VCC and VNN rail on SOC and MSIC losses
562 [SEC] Hig P2 Andr ramesh.agarwal@intel.com RESO DUPL charger diconnected => still show charging info in uevent
1392 [SEC] Hig P2 Andr fabricex.sorel@intel.com NEW 0001722: [Telephony]can not render any webpage after phone's re-camp the network.
ID Sev Pri OS Assignee Status Resolution Title
648 [SEC] Hig P2 Andr santhosh.k.reddy.s@intel.com RESO FIXE [PnP] Three JTAG clock signals consume total of 1.76 mA in S0i3 via FLIS settings for 2k pull-up resistors
1326 [SEC] Hig P2 Andr jianli.zhang@borqs.com RESO DUPL [Call] No audio on call (PR1)
697 [SEC] Hig P2 Andr petrix.harri@intel.com RESO FIXE Too many logs during data transfer
1465 [SEC] Hig P2 Andr hongyu.zhang@intel.com ASSI Camera physical shutter key does no work.
1431 [SEC] Hig P2 Andr lakshmi.n.vinnakota@intel.com RESO INVA alsa_arecord utility is crashing while recording loud voice for dual channel by using AMIC.
706 [SEC] Hig P2 Andr guillaumex.lucas@intel.com RESO FIXE SIM Toolkit freeze with Orange french SIM card
1283 [SEC] Hig P2 Andr dongsheng.zhang@intel.com ASSI System die when copy file about 900M
1183 Med P2 Andr honorex.tricot@intel.com ASSI wireless AP appear and disapper in scan list round and round
909 Med P2 Andr guillaumex.lucas@intel.com RESO FIXE 3GPP conformance - 31.124 - 27.22.6.2 Seq 2.1
915 Med P2 Andr jurgen.von.oerthel@intel.com ASSI View finding - preview effects do not change the appearance of the video recording
666 [SEC] Med P2 Andr zhengliex.song@intel.com RESO DUPL [Video]"AudioTrack( 1282): obtainBuffer timed" message when doing playback stress test
1119 Med P2 Andr elaine.wang@intel.com REOP Video Encode Profile Level in header info isn't correct.
656 [SEC] Med P2 Andr jack.ren@intel.com ASSI Need to define OS/Driver behavior in response to IMR violation MSI
584 [SEC] Med P2 Andr nicolas.roux@intel.com ASSI [OSPM] Entering S0i3 mode crashes the platform
897 Med P2 Andr sylvestrex.dischamp@intel.com ASSI cell properties not updated after a voice call handover
1385 [SEC] Med P2 Andr xiaolin.zhang@intel.com RESO FIXE Camera app hangs when low resolution video mode selected
994 Med P2 Andr frederic.predon@intel.com RESO DUPL contact in SIM card could not be found/imported
902 Med P2 Andr christophex.lebouc@intel.com RESO FIXE Darker OSR SplashScreen while flashing the OS
948 Med P2 Andr nicolas.roux@intel.com NEW [PnP] MSIC VPROG2 needs to be shut off when not being used including case of S0i3 when display is not active.
911 Med P2 Andr jean-christophe.sinet@intel... RESO WONT Cellular RF current consumption high while in call
1260 [SEC] Med P2 Andr jurgen.von.oerthel@intel.com INTE FIXE 176x144 resolution video recording easy cause ISP timeout
1445 [SEC] Med P2 Andr sytze.klijnsma@intel.com ASSI Oscillation of Auto White Ballance
1053 Med P2 Andr yaney.rodriguez@intel.com REOP Battery and Charger sysf shows incorrect value for MDFLD_ANDROID 20110308 Ginger Bread Build
403 [SEC] Med P2 Andr cyril.germond@intel.com ASSI Earpiece not working on some enclosed PR1 BB2 boards
765 [SEC] Med P2 Andr alexandre.lewicki@intel.com RESO FIXE WLAN: CRDA requirements for P_IUC_5118
836 [SEC] Med P2 Andr shuguang.gong@intel.com RESO FIXE V4L2 ENUMINPUT IOCTL cannot enum the secondary camera.
951 Med P2 Andr liang.l.yang@intel.com RESO FIXE Secondary Camera not displaying the proper position of the image.
667 [SEC] Med P2 Andr dan.liang@intel.com ASSI [Video] "Unable to create audio track" error happens during playing some high fps H264 video clips
755 [SEC] Med P2 Andr fabricex.sorel@intel.com ASSI 0000982: [BKB2]Mute can not work well during calling
597 [SEC] Med P2 Andr ramesh.babu@intel.com RESO WORK Headset re-plug not detected during voice call
566 [SEC] Med P2 Andr yuanx.xu@intel.com RESO FIXE [Video] Messy thumbnail shows up on some H264 Level 1.x clips
704 [SEC] Med P2 Andr nicolas.petit@intel.com ASSI reduce debug noise in config files
901 Med P2 Andr frederic.predon@intel.com RESO FIXE sms class 2 sms not received occasionally
912 Med P2 Andr eric.morel@intel.com ASSI 3GPP conformance : registration issue on RF test 34.121 7.8.5
903 Med P2 Andr jean-christophe.sinet@intel... RESO WONT RF FEM current selftest is unreliable
923 Med P2 Andr christophex.lebouc@intel.com RESO DUPL Penwell UART_0_CTS intermediate voltage level issue at Medfield platform boot up
997 Med P2 Andr nicolas.roux@intel.com NEW [PnP] S0 residency is 7% during S0i3 Vs target is 1% for S0i3 will hit M4 power targets
496 [SEC] Med P2 Andr madhusudanx.n.bangalore@int... RESO FIXE [Camera] 'Color Effect' is not restored after capturing (with any 'Color Effect'), saving & displaying that image.
838 [SEC] Med P2 Andr celinex.chotard@intel.com ASSI [Video] 1 out of 20 tries got error message when playback H263 video AMR audio
446 [SEC] Med P2 Andr al.bettner@intel.com REOP CWS: USB to Ethernet converter does not work. Need Ethernet interface for WiFi conformance testing.
898 Med P2 Andr renaudx.senet@intel.com ASSI [PnP] 2G & 3G IDLE / Modem sub system high power consumption
1447 [SEC] Med P2 Andr sytze.klijnsma@intel.com ASSI Auto exposure keeps on adjusting
946 Med P2 Andr yaney.rodriguez@intel.com NEW [PnP] VAUDA needs to be proactively shut off when not in use
669 [SEC] Med P2 Andr weian.chen@intel.com RESO FIXE [Video]Frames fail to show up on some Level>=30 H263 media clips
796 [SEC] Med P2 Andr chi.ding@intel.com ASSI [Video] ipp_aac_dec returns erron and causes system freeze when play .3gp 25 times
763 [SEC] Med P2 Andr jason.m.bills@intel.com ASSI power key to start PR1 should be removed to use ACS
1397 [SEC] Med P2 Andr shuo.liu@intel.com ASSI [Video] capabilities of supporting >50fps H263 codecs failed
786 [SEC] Med P2 Andr asit.kumar.verma@intel.com NEW [PnP] Regression on power consumption on ¡°VCCPADXXXAON_1P20¡± rail
804 [SEC] Med P2 Andr suhail.ahmed@intel.com INTE FIXE HSI controller must not enable timeout error handling for DMA operations
1368 [SEC] Med P2 Andr fabricex.sorel@intel.com ASSI 0001796: [Calling] ADN cannot be used.
1070 Med P2 Andr asit.kumar.verma@intel.com RESO FIXE [PNP Android]: avg power V_1P22_VCCAON_DSI for rail is @ 1.2 mW higher then targets
653 [SEC] Med P2 Andr christophex.lebouc@intel.com RESO FIXE XML Workaround for Bug 3149160 - 20k PD on SDIO_WP pin is not reliable
1269 [SEC] Med P2 Andr sanyog.r.kale@intel.com RESO WONT There is noise when play the stream recorded by calling interface "pcm.AndroidCapture_BuiltinMic_normal"
1309 [SEC] Med P2 Andr yu.y.xia@intel.com INTE FIXE exposure compensation doesn't work as expected
1377 [SEC] Med P2 Andr sundar.iyer@intel.com NEW Add dependency for MSIC_GPADC driver for the thermal driver
1243 [SEC] Med P2 Andr zheng.ba@intel.com RESO WORK After take a picture, before the next preview, the screen will become splash screen for a while.
1418 [SEC] Med P2 Andr jayant.mangalampalli@intel.com ASSI DUT reboots when running secureIPC test suite
896 Med P2 Andr sylvestrex.dischamp@intel.com RESO FIXE CardIdentifier disappears from SimManager properties after PIN query
904 Med P2 Andr jean-christophe.sinet@intel... ASSI 3GPP conformance : some HSUPA RF performance tests fails
477 [SEC] Med P2 Andr wei.gao@borqs.com ASSI [Camera] The mechanical capture button (to capture the image) doesn¡¯t work.
918 Med P2 Andr laurentx.fert@intel.com NEW [pnp] max3110 issue to bypass
705 [SEC] Med P2 Andr jackx.w.lix@intel.com RESO FIXE Signal STK session end not correctly done
1396 [SEC] Med P2 Andr jurgen.von.oerthel@intel.com ASSI Auto Focus function works but is not accurate.
511 [SEC] Med P2 Andr madhusudanx.n.bangalore@int... RESO FIXE [Camera] In the Viewfinder mode the popup menus does NOT rotate with the rotation of the device.
497 [SEC] Med P2 Andr saadi.maalem@intel.com RESO WONT [Security]There is no PUK input UI to unlock the SIM lock when the wrong pin is inputted 3 times.
1162 Med P2 Andr li.zeng@intel.com RESO FIXE [PnP] Gfx driver initiate suspend to OSPM eventhough VED/VEC/GL3 IP's not in suspended mode
1360 [SEC] Med P2 Andr li.zeng@intel.com ASSI [Video] Mosaics appeared while playing some H264 Level3 720P video clips
1353 [SEC] Med P2 Andr cyrillex.nivelle@intel.com NEED The process android.process.acore has stopped unexpectedly
533 [SEC] Med P2 Andr newfel.harrat@intel.com ASSI [Video] Should be able to support VP8 video codec
1320 [SEC] Med P2 Andr fabienx.peix@intel.com RESO INVA BasicAdapterTest#test_enableDisable from Android CTS fails
646 [SEC] Med P2 Andr christophex.lebouc@intel.com RESO FIXE Firmware: Enable fast strings by default
806 [SEC] Med P2 Andr panneer.s.arumugam@intel.com RESO FIXE [Video] Playback speed of MP4 with combination of H264/eAAC+(HE-AAC v2) is slower than it should be
1138 Med P2 Andr hongyu.zhang@intel.com ASSI Camera can not encode some types of video in MFLD Android R4.3
517 [SEC] Med P2 Andr yuanx.xu@intel.com RESO FIXE The thumbnail of some H.264 Baseline Profile video clips not able to be displayed in Gallery
929 Med P2 Andr benoit.romieu@intel.com ASSI IFX MODEM : at+cpwroff or at+cfun=0 are not handled correctly on MUX channel
910 Low P2 Andr jayant.mangalampalli@intel.com ASSI 300K Extended FW fails during boot
907 Low P2 Andr sylvestrex.dischamp@intel.com ASSI Unexpected extra space in the AT command answer for requesting the device information
599 [SEC] Blo P2 Andr jinyun.zhang@borqs.com ASSI PnP: NO VOIP application in Android-Gingerbread image
1189 enh P2 Andr kerry.vander.kamp@intel.com ASSI Enabling Audience voice processor on FFRD through SFI Table
382 [SEC] enh P2 Andr livingston.tong@intel.com RESO FIXE BKB2 shuts down when the battery drops below 3.4v, even with charger connected all the time
1314 [SEC] enh P2 Andr dan.liang@intel.com ASSI [Video feature request] Need support .flv and .f4v file container with VP6/H264 video codec and mp3/AAC audio codec
802 [SEC] enh P2 Andr guillaumex.lucas@intel.com INTE FIXE Integration of the tethering capability
1173 enh P2 Andr jason.hu@intel.com ASSI [PnP] Dynamic support for overlay during video playback
1144 Hig P3 Andr jayant.mangalampalli@intel.com ASSI watchdog devel headers not in R4.3 source tree
1091 Hig P3 Andr christophex.lebouc@intel.com RESO FIXE "E50B" is displayed on SCU serial port LED
966 Hig P3 Andr alainx.kouassu@intel.com ASSI Concurrent execution of wget for large files results in premature termination or stall of the commands
826 [SEC] Hig P3 Andr nicholas.j.yoke@intel.com NEED Need kernel to handle MSI enabling when it comes up to avoid unhandled interrupts.
1135 Hig P3 Andr jayant.mangalampalli@intel.com ASSI POS: External CRYS ATP tests fail
1134 Hig P3 Andr mark.a.allyn@intel.com ASSI POS: External key manager (kmng) ATP tests fail
647 [SEC] Hig P3 Andr nicholas.j.yoke@intel.com RESO FIXE Core DTS reading keep bouncing in a range of 4c every sec when using Osc DTS and C4/C6 enabled part (TP-B0D1 YSUK)
1160 Hig P3 Andr pierre.tardy@intel.com NEW [PNP] Frequent wake ups caused by system_server in Android
1218 Hig P3 Andr mark.a.allyn@intel.com ASSI Request to provide validation with a mechanism to verify that MidCrypto engine is used by OpenSSL
1285 [SEC] Hig P3 Andr sanyog.r.kale@intel.com ASSI System die when audio recording
1133 Hig P3 Andr jayant.mangalampalli@intel.com ASSI POS: CC6_MW_ATP - multiple menu items dne, will not execute
873 Med P3 Andr christophex.lebouc@intel.com RESO DUPL FW: Disable HC Blocking DEBUG0[20] by default
1161 Med P3 Andr guoqiang.cao@intel.com ASSI [PnP] Gfx KPI - SimulationMark Binary not available
447 [SEC] Med P3 Andr wei.gao@borqs.com ASSI Two same camera photo folders are displayed after capturing a picture
1457 [SEC] Med P3 Andr bruce.j.beare@intel.com ASSI Android_disk build target does not build unless disk_installer target has been built
737 [SEC] Med P3 Andr jin.xiao@intel.com ASSI In China SH public network, no sim card, emergencycall fail when at+xbanbsel=1800
1164 Med P3 Andr lawrence.r.klos@intel.com ASSI [PnP] Gfx KPI - Targets for GLBench2.0 Not Avalable
ID Sev Pri OS Assignee Status Resolution Title
1462 [SEC] Med P3 Andr xiaolin.zhang@intel.com NEW Preview in image capture mode is stretched when setting the resolution to 16:9 ratio (720p/1080p) .
1363 [SEC] Med P3 Andr madar.sikkandar.d@intel.com RESO FIXE Power optimization: Music player need not wake up when display is off
631 [SEC] Med P3 Andr shanshanx.liu@intel.com INTE FIXE Can't adjust the volume of voice call by volume up/down key
749 [SEC] Med P3 Andr wei.gao@borqs.com ASSI [Video] Gallery fails to extract thumbnail clusters with "Texture creation fail" message
1370 [SEC] Med P3 Andr randy.xu@intel.com RESO FIXE the displayed notification scroll bar is not in the middle
730 [SEC] Med P3 Andr fredericx.berat@intel.com ASSI [MMS] Receiving MMS fails with french Orange SIM card
513 [SEC] Med P3 Andr madhusudanx.n.bangalore@int... ASSI [Camera] There is no Radio button for ¡°Restore to defaults¡± to restore the Camera Settings.
628 [SEC] Med P3 Andr chi.ding@intel.com ASSI Can not play audio file: AAC_HE_V2_16000Hz_mono.aac
921 Med P3 Andr tim.coppernoll@intel.com ASSI [pnp] port eMMC driver from Meego to Android
956 Med P3 Andr marcx.blassin@intel.com ASSI Impossible to remove modules with rmmod
1426 [SEC] Med P3 Andr josephx.gao@intel.com NEED "mkdosfs" creates a FAT32 system but should create FAT16 system
1155 Med P3 Andr yaney.rodriguez@intel.com NEW [PnP] SOC thermal Sensors rail "V_VCCTHMSOCSI0_1P80" is consuming 8mW power during Idle case
1177 Med P3 Andr weian.chen@intel.com RESO FIXE AVC encoder omx uses a constant size for buffers at the input port
1017 Med P3 Andr jason.m.bills@intel.com NEW SPI1 UART doesn't work in IA FW in BKB1.5
1156 Med P3 Andr juliex.regairaz@intel.com NEW [PnP] Browsing KPI - Browsing GSMA WLAN not meeting Platform Power target of 500mW
1185 Med P3 Andr khanh.v.nguyen@intel.com ASSI Medfield ES2: The player plays some audio clips, but has not sound in R4.3.
1141 Med P3 Andr jasonx.m.harper@intel.com RESO FIXE [PnP] Local MP3 Playback (Screen OFF) Power KPI not meeting power target of 172mW
652 [SEC] Med P3 Andr christophex.lebouc@intel.com ASSI FW: Enable_RTT_while_locked DEBUG1[4] by default
1188 Med P3 Andr panneer.s.arumugam@intel.com RESO FIXE Medfield ES2: The playback sound of some clips is different with the original sound in R4.3.
741 [SEC] Med P3 Andr dharageswari.r@intel.com RESO DUPL Listen to the music by wired headset, pull out the headset, resume the music, the music paused for 10 seconds abnormally, then re-play.
1180 Med P3 Andr lakshmi.n.vinnakota@intel.com RESO WORK Capture of audio files using DMIC4 is failing
1104 Med P3 Andr nicholas.j.yoke@intel.com NEW Provide a mechanism in wFSTK to auto populate keys
871 Med P3 Andr christophex.lebouc@intel.com RESO DUPL FW: Enable Hunit bypass HMISC1[7] by default
481 [SEC] Med P3 Andr randy.xu@intel.com ASSI [Image] Thumbnail of GIF_4320x2160_96dpi_8bit cannot be shown correctly in Gallery
874 Med P3 Andr christophex.lebouc@intel.com RESO DUPL FW: Enable_RTT_while_locked DEBUG1[4] by default
1005 Med P3 Andr jurgen.von.oerthel@intel.com ASSI SP initialization complete interrupt is missing
758 [SEC] Med P3 Andr wei.c.gao@intel.com ASSI 0001522: [Home] UI issue when hightlight on music wigdet
1163 Med P3 Andr guoqiang.cao@intel.com ASSI [PnP] Gfx KPI - BaseMark GUI (3D and Nav UI)
957 Med P3 Andr louis.le.gall@intel.com ASSI [new dev] allow bt modules to be loaded if no sco sink/src creatd + suspend BT sco sink&src if hsp profile not set
471 [SEC] Med P3 Andr wei.gao@borqs.com ASSI [Image] special character in JPG will cause media scanner dead
959 Med P3 Andr zuping.qin@intel.com ASSI PTI driver tests may experience crash on Froyo and Gingerbread MFLD
1366 [SEC] Med P3 Andr ping.liang@intel.com ASSI [Media scanner] media cranner makes error "waitForCondition timed out" with system hung
545 [SEC] Med P3 Andr thomasx.guillemin@intel.com RESO FIXE No signal and no 2G Icon while camped and downloading (iCDK ES2)
894 Med P3 Andr jing.tao@intel.com ASSI ov2720 quality: too many noise of output raw data
514 [SEC] Med P3 Andr madhusudanx.n.bangalore@int... ASSI [Camera] There is no menu option to select the ¡®Primary Camera¡¯.
1191 Med P3 Andr kerry.vander.kamp@intel.com ASSI Disabled clock gates need to be enabled in the firmware for Units B, D0, H and I.
958 Med P3 Andr marcx.blassin@intel.com ASSI Duplicate service definition in init.rc and init.device.rc
777 [SEC] Med P3 Andr shengquan.yuan@intel.com ASSI [Video] sqlite returns error with disk I/O error after repetitive playing one mp4 clip 30 times
1174 Med P3 Andr weian.chen@intel.com RESO FIXE AVC encoder omx component overwriting OMX_VIDEO_PARAM_PORTFORMATTYPE.nIndex
1336 [SEC] Med P3 Andr christophe.continente@intel... ASSI The pin can not be inputted because the input windows can not be focused.
1093 Med P3 Andr khanh.v.nguyen@intel.com ASSI (Audio) He aac codec stream can't be played
853 Med P3 Andr christophe.guerard@intel.com ASSI PROMOTE from penwell: PUnit security keys are not being sent after S0i2/S0i3
1082 Med P3 Andr timothy.c.dietz@intel.com NEW SCU FW Does Not Pass Manufacturing Mode Jumper Status to IA
751 [SEC] Med P3 Andr hitesh.k.patel@intel.com ASSI LCD Display color distorted
1186 Med P3 Andr khanh.v.nguyen@intel.com ASSI Medfield ES2: The speed of audio clips playback is quicker than normal in R4.3
650 [SEC] Med P3 Andr christophex.lebouc@intel.com ASSI FW: Enable RQArb Roll Enable DEBUG0[21] by default
876 Med P3 Andr nicholas.j.yoke@intel.com NEW D-unit register settings not optimized for power and performance
1434 [SEC] Med P3 Andr gangx.a.chen@intel.com RESO FIXE Play a song when in call via earpiece, the song can't be heard and the song can't be played correctly.
1390 [SEC] Med P3 Andr juliex.regairaz@intel.com RESO FIXE FTP transfers of 50MB+ files via WiFi fail to complete when using AndFTP client
866 Med P3 Andr livingston.tong@intel.com ASSI PROMOTE from penwell: AVE_CV: Unable to receive FM signal on Medfield iCDK platform during FM playback
1125 Med P3 Andr dharageswari.r@intel.com RESO DUPL There is white noise when call pcm.AndroidCapture_Headset_normal to capture a piece of audio
776 [SEC] Med P3 Andr christophex.lebouc@intel.com RESO DUPL System Boot failed
1092 Med P3 Andr livingston.tong@intel.com ASSI msvdx motion vector silicon bug causes corruption for 1920x1080 mpeg4 clip when playing on the MFLD Android 20110318
945 Med P3 Andr bin.yang@intel.com NEW I2C frequency is measured as 407Khz at fast mode
1416 [SEC] Med P3 Andr ramesh.babu@intel.com ASSI [Audio accessory] The micro of headset is not detected
721 [SEC] Med P3 Andr xiaolin.zhang@intel.com RESO WORK 0001579: Phone hang during boot up.
872 Med P3 Andr christophex.lebouc@intel.com RESO DUPL FW: Enable RQArb Roll Enable DEBUG0[21] by default
1406 [SEC] Med P3 Andr bingx.deng@intel.com RESO FIXE After refusing the MT call, the song is outputted from Speaker&wired headset instead of only wired headset.
1401 [SEC] Med P3 Andr shanshanx.liu@intel.com ASSI When play the recorded audio via wired headset with mic, the sound is too small to be heard.
720 [SEC] Med P3 Andr gang.a.hu@intel.com RESO FIXE Camera does no response.
661 [SEC] Med P3 Andr mariex.petit@intel.com RESO FIXE Medfield Android R4.3 Release Notes do not have clear and adequate Android load instructions
1372 [SEC] Med P3 Andr christophe.continente@intel... NEW No response to sliding when running the application Aldiko
773 [SEC] Med P3 Andr gang.a.hu@intel.com RESO FIXE Camera will crash, when switch between photographed mode and camera mode some times
885 Med P3 Andr jason.m.bills@intel.com ASSI Lock Dual Channel Bit in the BCTRL register of B unit is not set in the C0 PO FW
1088 Med P3 Andr timothy.c.dietz@intel.com RESO DUPL [PnP] Enabling D0i3/D3 on LPE (LSS8) increase power on "VCCPADXXXAON_1P20" by ~7mW
1379 [SEC] Med P3 Andr arulselvan.m@intel.com RESO INVA When a audio file is played on earpiece just after boot, the audio is heard on both Headset and Earpiece
1122 Med P3 Andr khanh.v.nguyen@intel.com ASSI Medfield ES2: The player does not support some types of audio files.
1345 [SEC] Med P3 Andr weian.chen@intel.com ASSI [Video] Got black screen with OMXCodec error during video playback
1316 [SEC] Med P3 Andr kishore.mottadi@intel.com NEW Battery status do not change to Full when it is completely charged.
651 [SEC] Med P3 Andr christophex.lebouc@intel.com ASSI FW: Disable HC Blocking DEBUG0[20] by default
654 [SEC] Med P3 Andr yong.yao@intel.com RESO FIXE D-unit self-refresh bit in C0 not enabled in BIOS
1179 Med P3 Andr lakshmi.n.vinnakota@intel.com RESO WORK Capture of audio files using DMIC3 is failing
1278 [SEC] Med P3 Andr xiaokang.qin@intel.com INTE FIXE Please help to unify partition name both POS and Android
655 [SEC] Med P3 Andr christophex.lebouc@intel.com RESO FIXE R.O. core DTS needs to enable binary search mechanism by default to converge temperature
1427 [SEC] Med P3 Andr jianpingx.li@intel.com RESO FIXE Rebase omx-compent decode code
981 Low P3 Andr randy.xu@intel.com RESO INVA Mfld: 2D_X: EXA Extension-repeat test failed - 134 of 136 tests passed.
891 Low P3 Andr adityax.gadgil@intel.com ASSI Audio goes silent if gst alsasink latency-time is > 100000
949 Low P3 Andr livingston.tong@intel.com ASSI AvP MSIC Coulomb Counter Total-error not meeting specifications.
1099 Low P3 Andr jenny.tc@intel.com ASSI adc_temperature interface not found in Medfield_Android_ROW_20110318-003 build
980 Low P3 Andr michael.h.chen@intel.com RESO INVA Mfld: 2D_X: Xproto test failed - 230 tests pass, 1 fewer than the 231 tests that pass in reference result.
965 Low P3 Andr frederic.predon@intel.com RESO WONT /dev/ttyIFX might not be integrated properly on HSI Medfield Android R4.3
1007 Low P3 Andr yaney.rodriguez@intel.com NEW sysfs current_now of msic-battery is always constant.
563 [SEC] Low P3 Andr dominique.grange@intel.com ASSI after MaintenanceCharging status stay full when charger is dis and re connect
1140 enh P3 Andr nicolas.roux@intel.com ASSI [METABUG_KPI] Active Idle (Screen ON) Power KPI not meeting power target of 458mW
1149 enh P3 Andr nicolas.roux@intel.com ASSI [METABUG_KPI] Standby KPI - GSM standby not meeting Platform Power target of 12.5mW
1184 enh P3 Andr nicolas.roux@intel.com ASSI Cstate values are inconsitent
672 [SEC] enh P3 Andr christophe.guerard@intel.com ASSI Modem log can not be captured by Lauterbach with MPTA
961 enh P3 Andr hervex.marechal@intel.com ASSI 6260 FW change for tracing to accomidate Medfield HW arch
1287 [SEC] enh P3 Andr austin.hu@intel.com ASSI Placeholder for HDMI extend video use case support
1344 [SEC] enh P3 Andr xiaokang.qin@intel.com INTE FIXE To support Modem FW update in OTA
1466 [SEC] enh P3 Andr hongyu.zhang@intel.com NEW Share buffering not enabled in video capture
1142 enh P3 Andr nicolas.roux@intel.com ASSI [METABUG_KPI] Multimedia, Video playback - h.264 - HP - 1080p->720p 30fps Power KPI not meeting Power taget of 863mW
1150 enh P3 Andr nicolas.roux@intel.com ASSI [METABUG_KPI] Standby KPI - WLAN associated standby not meeting Platform Power target of 14.5mW
756 [SEC] enh P3 Andr vanja.rados@intel.com REOP 0001549: [Tele]can not import contacts from SIM card.
1358 [SEC] enh P3 Andr xiaokang.qin@intel.com ASSI Add Factory Restore support in PrOS
930 enh P3 Andr elaine.wang@intel.com ASSI [PnP] High C2 during 1080p 30 FPS video playback without audio
1148 enh P3 Andr nicolas.roux@intel.com ASSI [METABUG_KPI] Standby KPI - WCDMA standby not meeting Platform Power target of S3-13.5mW; S0i3-16.5
1139 enh P3 Andr nicolas.roux@intel.com ASSI [METABUG_KPI] Active Idle (Screen OFF) Power KPI not meeting power target of 95mW
1435 [SEC] enh P3 Andr renaudx.senet@intel.com NEW [metabug]: Modem consumption optimization
1151 enh P3 Andr nicolas.roux@intel.com ASSI [METABUG_KPI] Browsing KPI - Browsing GSMA 3G WCDMA not meeting Platform Power target of 505mW
ID Sev Pri OS Assignee Status Resolution Title
1331 [SEC] enh P3 Andr jasonx.m.harper@intel.com ASSI Use OpenMAX audio software codec components to reduce power consumption
1359 [SEC] enh P3 Andr xiaokang.qin@intel.com ASSI OSIP update tool enhancement
1319 [SEC] enh P3 Andr yuanx.zhao@intel.com INTE FIXE DLC5 is allocated to atproxy, but used by Audio Hal
662 [SEC] Cri P4 Andr leo.he@borqs.com RESO FIXE IA32 CPU Firmware hung
1273 [SEC] Hig P4 Andr shenghua.lu@intel.com ASSI playing music while have the lcd backlight turned dark,the music stop
695 [SEC] Hig P4 Andr juliex.regairaz@intel.com RESO FIXE WLAN : WEP Open connection failure
803 [SEC] Hig P4 Andr suhail.ahmed@intel.com INTE DUPL HSI protocol handler makes TTY interface when SPI is enabled
1274 [SEC] Hig P4 Andr sylvestrex.dischamp@intel.com ASSI Data drop during CPC activation - deactivation
828 [SEC] Hig P4 Andr danielx.lee@intel.com RESO DUPL Enter into soi3 unsuccessful[PmP]
809 [SEC] Hig P4 Andr jian.a.zhu@intel.com RESO DUPL 0001605: sometimes stk app icon won't show after phone boot up
1263 [SEC] Hig P4 Andr jasonx.m.harper@intel.com RESO FIXE mp3 file with cover (image/jpg) can not be played normally
768 [SEC] Hig P4 Andr olivier.leveque@intel.com RESO FIXE TIWLAN SDIO interface unreliable with 50 MHz clock
1098 Hig P4 Andr lakshmi.n.vinnakota@intel.com RESO INVA HSMIC option is not available in alsa_amixer.
761 [SEC] Hig P4 Andr petrix.harri@intel.com RESO FIXE TIWLAN module leaves powered on at the boot despite never turned on from the UI
770 [SEC] Hig P4 Andr petrix.harri@intel.com RESO FIXE [WiFi] The TI WLAN driver and module should be under control of Android native connectivity control
539 [SEC] Hig P4 Andr marcx.blassin@intel.com RESO FIXE Can NOT CAMP on ORANGE and BOUYGUES TELECOM Network
580 [SEC] Hig P4 Andr srivathsan.soundararajan@in... RESO WONT No fallback mechanism in case of RAT change failure
771 [SEC] Hig P4 Andr suhail.ahmed@intel.com RESO DUPL Need registration entry for GPIO info in mrst.c
1238 [SEC] Hig P4 Andr fengx.xiao@intel.com RESO FIXE AVC/H264 IDR frame data should contains sps & pps data and new NALU start code support for stagefright config data parser from first frame header
762 [SEC] Hig P4 Andr petrix.harri@intel.com RESO FIXE TIWLAN driver module can not be re-instantiated
701 [SEC] Med P4 Andr nicolas.petit@intel.com RESO DUPL CWS WLAN: Failed to connect and stay connected for 12 Hrs
1256 [SEC] Med P4 Andr sushma.singh@intel.com RESO INVA BT_PBAP: Car kit can not access contacts in Phone
1225 [SEC] Med P4 Andr vincentx.pillet@intel.com ASSI The browser crashed after several times normal web browsing
839 [SEC] Med P4 Andr zhenjie.pan@intel.com RESO FIXE Besides 30GB filesystem, other partitions are also mounted to PC.
1253 [SEC] Med P4 Andr sylvestrex.dischamp@intel.com ASSI Modem alters loopback audio data on I2S2
443 [SEC] Med P4 Andr haijun.cao@intel.com RESO WONT Sensor Hub Latency is too long from application in concurrence mode
1261 [SEC] Med P4 Andr shanshanx.liu@intel.com RESO DUPL Firmware error code is "F503" when play music via BlueTooth Headset
1046 Med P4 Andr ganeshx.petkar@intel.com RESO WORK File playback by alsa_aplay with given option(alsa_aplay s_48k_24.raw -c2 -r 48000 -fs24_le -traw -Dhw:0,0) is not working.
767 [SEC] Med P4 Andr jason.hu@intel.com ASSI [Video] Sometimes, MKV H264 (AAC audio) video playback fails
1233 [SEC] Med P4 Andr jeanx.trivelly@intel.com ASSI WLAN : WPS support
722 [SEC] Med P4 Andr gang.a.hu@intel.com RESO FIXE Video Camera can not display normal when recording.
1020 Med P4 Andr khanh.v.nguyen@intel.com ASSI Playback of AAC format audio file in the media player is failing
775 [SEC] Med P4 Andr gang.a.hu@intel.com RESO DUPL Video Camera would die after video recording some times.
1171 Med P4 Andr gang.a.hu@intel.com RESO DUPL System hang when capture image continuously.
1102 Med P4 Andr timothy.c.dietz@intel.com ASSI Mfld/Android: OSPM: state changes occur but SPI Card LED code never changes from 5017 to expected values
822 [SEC] Med P4 Andr daniel.zhu@intel.com ASSI [PnP] Low UDP uplink throughputs in USB
1193 Med P4 Andr christophe.guerard@intel.com ASSI Unable to bringup Android Signed/unsigned OS boot.bin with secure signed android kboot
843 [SEC] Med P4 Andr wen.w.wang@intel.com NEW Noise Reduction has no effect with OV2720 camera.
649 [SEC] Med P4 Andr christophex.lebouc@intel.com ASSI FW: Enable Hunit bypass HMISC1[7] by default
1084 Med P4 Andr gang.a.wang@intel.com ASSI Mfld/Android/GB: GLES2.0 Conformance - 2 cases fail
603 [SEC] Med P4 Andr yong.yao@intel.com RESO FIXE [WLAN] All boards have same MAC address
1168 Med P4 Andr yu.y.xia@intel.com RESO FIXE Flash light did not work when capture image with Medfield Android application.
769 [SEC] Med P4 Andr petrix.harri@intel.com ASSI [TIWLAN] WLAN chip unusable with 50 MHz SDIO bus clock (SW point of view)
1221 Med P4 Andr yun.tu@intel.com ASSI GFX_PERF: 3DMMES2.0: some white artifacts/corruption about 5-10 seconds into Taiji game bench
848 [SEC] Med P4 Andr sylvestrex.dischamp@intel.com ASSI 3GPP Conformance - 12.2.1.5d test case (TS 3GPP 34.123) is failing because modem stucks after AT+CGATT=1
644 [SEC] Med P4 Andr nicolas.roux@intel.com ASSI Seeing a hot spot in the ULPIMSIC module when in System states
990 Med P4 Andr randy.xu@intel.com RESO FIXE Mfld (Android): GFX-PM - PM Service available test failed
1211 Med P4 Andr lawrence.r.klos@intel.com NEW Mfld/Android/GB: GFX-PM - system not waking up by touching screen or plugging/unpluging headphone jack
1081 Med P4 Andr jean-mariex.bellouard@intel... RESO FIXE when playing on alsa devices with aplay: driver reaches max stream count then board is frozen
1067 Med P4 Andr shanshanx.liu@intel.com ASSI After run cts for some time, the Android OS hangs up
1043 Med P4 Andr ganeshx.petkar@intel.com ASSI click noise at the end of playback of wav or raw file.
817 [SEC] Med P4 Andr li.zeng@intel.com REOP Crc value of some vc1 clips calculated by cdk is different with VXDSIM
1262 [SEC] Med P4 Andr shanshanx.liu@intel.com ASSI When Ringtone rings with BT A2DP headset, the system alert happens, but the alert delayed 10 seconds outputed from BT headset than Speaker
818 [SEC] Med P4 Andr jason.hu@intel.com VERI FIXE Function vaCreateSurfaces() failed after vaDestroySurfaces() and vaTerminate() failed several times
1100 Med P4 Andr yaney.rodriguez@intel.com NEW For MDFLD_Android_ROW, the Peak Current Control driver's sysfs interface "action_mask" accepts out of range values.
1235 [SEC] Med P4 Andr weian.chen@intel.com RESO FIXE merge libmix
781 [SEC] Med P4 Andr fabienx.barthes@intel.com ASSI [Audio] Midi file with Xmf container cannot be played
759 [SEC] Med P4 Andr juliex.regairaz@intel.com RESO FIXE Can not connect wifi network
1251 [SEC] Med P4 Andr gang.a.hu@intel.com INTE FIXE Double click the touch screen cause camera application crash during viewfinder
1230 [SEC] Med P4 Andr juliex.regairaz@intel.com ASSI WLAN : WAPI support
739 [SEC] Med P4 Andr lili.a.wang@intel.com RESO FIXE [Video] Thumbnails of some H264 main and high profile video clips cannot be show in Gallery
467 [SEC] Med P4 Andr yong.yao@intel.com RESO FIXE SD card insertion failure
841 [SEC] Med P4 Andr wen.w.wang@intel.com NEW Black Level Compensation has no effect with OV2720 camera.
1228 [SEC] Med P4 Andr kun.k.wang@intel.com RESO FIXE Port the latest libva library to MFLD android Gingerbread
466 [SEC] Med P4 Andr xiaokang.qin@intel.com REOP boot to command prompt from USB Memory stick (with kboot on eMMC)
614 [SEC] Med P4 Andr ramesh.babu@intel.com RESO FIXE [Audio]play audio files faster than normal.
1111 Med P4 Andr jayant.mangalampalli@intel.com ASSI Chaabi UMIP read fails on some combinations of offset and size.
703 [SEC] Med P4 Andr vgonzalez@intrinsyc.com ASSI Failed to set airplane mode when no SIM card in the device.
683 [SEC] Med P4 Andr nicolas.petit@intel.com RESO FIXE BT not enable at boot as well as it was on at switch off
673 [SEC] Med P4 Andr frederic.predon@intel.com RESO FIXE Airplane mode can¡¯t be set successfully
845 [SEC] Med P4 Andr jurgen.von.oerthel@intel.com NEW Digital Zoom running in ISP primay mode dosn't have effect for RGB565 and dual stream
1167 Med P4 Andr jurgen.von.oerthel@intel.com ASSI incorrect judgement for flash on/off in auto flash mode in 3A source code
772 [SEC] Med P4 Andr wei.c.gao@intel.com ASSI Can not repeatedly take pictures
1169 Med P4 Andr xiaolin.zhang@intel.com RESO FIXE The color effect options in the camera application did not work.
442 [SEC] Med P4 Andr haijun.cao@intel.com RESO WONT Sensor Hub Latency is too long from application layer
1089 Med P4 Andr jing.a.sun@intel.com NEW eMMC Chip's HW reset triggered by its drivers when data timeouts happened might have a bad effect on other ingredients.
785 [SEC] Med P4 Andr nicolas.roux@intel.com RESO FIXE Power: Current on PADEMC (1p80AON) rail is higher in forced S0i3 state when using POR FW compared to Custom FW (2.31mA vs 97uA)
991 Med P4 Andr randy.xu@intel.com RESO FIXE Mfld (Android): GFX-PM - Early suspend test failed
1332 Med P4 Andr lawrence.r.klos@intel.com RESO WONT Mfld/Android: GFX_PERF: Significantly lower perf scores on various tests than in previous ENG build 5.4.0.1003
1197 Med P4 Andr randy.xu@intel.com RESO FIXE [patch] Use the bottom page of KERN_DATA_HEAP for GL3_USSE_WR_ADDR
1237 [SEC] Med P4 Andr shanshanx.liu@intel.com NEED Sometimes there is no sound outputed from BlueTooth Headset when make screen selection.
1044 Med P4 Andr ganeshx.petkar@intel.com RESO WORK we see warning message while playback using alsa_aplay command
699 [SEC] Med P4 Andr al.bettner@intel.com ASSI CWS WLAN: [Android] Cycle back between two APs several times then DUT always displays connect to the same AP.
1210 Med P4 Andr christophex.lebouc@intel.com NEW Medfield B0 ICDK/ CEAK platform cannot be reliably detected with a 6 ft. USB cable.
1232 [SEC] Med P4 Andr jeanx.trivelly@intel.com RESO FIXE WLAN : WPA Enterprise
975 Med P4 Andr saadi.maalem@intel.com RESO FIXE XML needs to be updated (GPIO Slew Setting): I2C3 Port with 16.6MHz Controller frequency the Hold time Clock Fall 30% to Data Rise 30% fail EMTS spec.
1170 Med P4 Andr gang.a.hu@intel.com RESO FIXE When capture video with "low" and "mms" resolution, the viewfinding and recorded video are all invisible.
642 [SEC] Med P4 Andr daniel.zhu@intel.com ASSI [PnP] Very low USB copy throughput
842 [SEC] Med P4 Andr wen.w.wang@intel.com NEW Edge Enhancement has no effect with OV2720 camera.
1015 Med P4 Andr jasonx.m.harper@intel.com RESO FIXE [Medfield-Android]: "music playback forward seek relative" shows abnormal
724 [SEC] Med P4 Andr lindax.lin@intel.com ASSI Sending larger file(4GB) uplink from iCDK ES2 to laptop failed.
1399 [SEC] Med P4 Andr jianchunx.shen@intel.com RESO FIXE Audio StreamIn Standby issue, without actualizing in HAL
1229 [SEC] Med P4 Andr kun.k.wang@intel.com RESO FIXE Port the latest psb_video library to MFLD Android Gingerbread
686 [SEC] Med P4 Andr nicholas.j.yoke@intel.com RESO FIXE Penwell UART_0_CTS intermediate voltage level issue at Medfield platform boot up
805 [SEC] Med P4 Andr suhail.ahmed@intel.com INTE FIXE Modem reset and crash dump signals must be handled properly for modem boot and silent reset
1271 [SEC] Med P4 Andr wen.w.wang@intel.com ASSI Still Camera consuming ~530mW in some runs during system Idle case
1241 [SEC] Med P4 Andr suhail.ahmed@intel.com ASSI AP SW log can¡¯t be collected through UART.
468 [SEC] Med P4 Andr gareth.yu@intel.com ASSI Change USB interface with PID
798 [SEC] Med P4 Andr christophex.lebouc@intel.com ASSI Fail to boot from dead battery
1429 [SEC] Med P4 Andr sebastien.cayetanot@intel.com ASSI 0001862: [BKB2][Bluetooth]Can not enable bluetooth successfully by the first time after flash the phone.
ID Sev Pri OS Assignee Status Resolution Title
820 [SEC] Med P4 Andr vgonzalez@intrinsyc.com ASSI Call Barring not working when class is not filled
1060 Low P4 Andr fredericx.berat@intel.com ASSI Can't activate call waiting during a voice call
823 [SEC] Low P4 Andr jeanx.trivelly@intel.com ASSI WLAN: UI for WPA/WPA2 Enterprise is misleading
1250 [SEC] Low P4 Andr ramesh.agarwal@intel.com NEW [Battery] The counter runs faster during battery discharge
1074 Low P4 Andr jayant.mangalampalli@intel.com ASSI Firmware Arch Spec says Chaabi code includes Version info but they do not.
743 [SEC] Low P4 Andr fredericx.berat@intel.com ASSI RIL_REQUEST_SEND_SMS_EXPECT_MORE not used for long SMS
824 [SEC] Low P4 Andr jeanx.trivelly@intel.com ASSI WLAN: WPA/WPA2 Enterprise - Issue when switching between PEAP and TTLS methods
746 [SEC] Low P4 Andr gang.a.hu@intel.com RESO FIXE [camera] camera app does not recover from ISP timeout/csi reciever error
1286 [SEC] Low P4 Andr li.zeng@intel.com RESO FIXE [Video] First few frames display black screen when playing some H264 video clips
1267 [SEC] Low P4 Andr saadi.maalem@intel.com NEW Texture streaming error seen in the preview log
1045 Low P4 Andr rajesh.poornachandran@intel... ASSI Taskforce: Mtfld-Android No Driver with D0i3/D3 for HDMI
835 [SEC] Low P4 Andr fabienx.peix@intel.com ASSI Pairing code input timeout too short
1016 Low P4 Andr sebastien.cayetanot@intel.com ASSI Duplicate service definition in init.rc and init.device.rc
598 [SEC] Low P4 Andr louis.le.gall@intel.com ASSI 2-3Hz glitches during voice call
1279 [SEC] Low P4 Andr jin.b.zhang@intel.com ASSI The boot failed only one time with "AudioPolicyService not published"
487 [SEC] Low P4 Andr yan.a.wang@intel.com REOP boot to command prompt from SD card (with kernel on eMMC) unstable issue
970 Low P4 Andr kerry.vander.kamp@intel.com ASSI IA FW v26 - Programs OS Image to eMMC before HASH verification
1108 Low P4 Andr yaney.rodriguez@intel.com RESO DUPL current temeprature value in temp sysfs interfaces of thermal zones remains constant for MDFLD_Android_20110318-003
1096 Low P4 Andr rajesh.poornachandran@intel... ASSI [Taskforce]Display doesn't come back reliably on S3 exit
478 [SEC] Low P4 Andr yong.yao@intel.com RESO FIXE Set Bluetooth Mac address failure
931 Low P4 Andr livingston.tong@intel.com NEW IFWI Public keys reversed compared to FAS
969 Low P4 Andr bin.yang@intel.com ASSI IPC failed message during long duration wav playback
1234 [SEC] Blo P4 Andr juliex.regairaz@intel.com ASSI WLAN : CRDA support
570 [SEC] enh P4 Andr philippe.lemoine@intel.com ASSI P_IUC_1901 Audio Listen FM Radio - wired HS
793 [SEC] enh P4 Andr louis.le.gall@intel.com REOP I2S/PCM ports of Modem and MSIC not disabled after voice call
640 [SEC] enh P4 Andr pierre.tardy@intel.com ASSI PnP:Standby power KPI "Standby Flight Mode-S3" is not meeting PV targets of 9mW
825 [SEC] enh P4 Andr selma.bensaid@intel.com ASSI PWL I2S_1 port to be set as master for voice playback and recording over Bluetooth headset
1249 [SEC] enh P4 Andr frederic.predon@intel.com NEW Integration and test of Customer AT Commands extensions
619 [SEC] enh P4 Andr jingtaox.wang@intel.com RESO WONT "Music" can't scan the stream file: ap02_LTP--AAC_128Kbps_2c_48KHz_19s.mp4
1231 [SEC] enh P4 Andr richard.tang@intel.com ASSI [PnP] Regression found from GB0330 to WW15 build , i2c-dw-pci-5 interrupt jump from 0 to 60
1268 [SEC] enh P4 Andr jason.m.bills@intel.com ASSI Errata in IA FW 00.37 Release Notes
1341 [SEC] enh P4 Andr fabienx.marotte@intel.com ASSI D-BUS path activation between wpa_supplicant and WDAgent
1254 [SEC] enh P4 Andr juliex.regairaz@intel.com NEW WLAN : 5GHz band support
620 [SEC] enh P4 Andr jianjiang.fei@borqs.com RESO WONT 0001539: [Framework]the numbers may flash after switch back.
1240 [SEC] enh P4 Andr hongyu.zhang@intel.com RESO FIXE Video buffer sharing flag in camera HAL not enabled
636 [SEC] enh P4 Andr nicolas.petit@intel.com RESO FIXE Wifi calibration file to add
1361 [SEC] enh P4 Andr xiaokang.qin@intel.com ASSI scuutils: Disable actual pm before firmware update
709 [SEC] enh P4 Andr guillaumex.lucas@intel.com RESO FIXE Enable TTY support in Gingerbread
1391 [SEC] enh P4 Andr bingx.deng@intel.com INTE FIXE Need design a new lock in alsa_asound directory to replace the old lock.
847 [SEC] enh P4 Andr jack.ren@intel.com ASSI music file failed to be played when it is in SD card of MFLD iCDK board
693 [SEC] enh P4 Andr jackx.w.lix@intel.com RESO FIXE Rapid RIL : TTY read AT commands is not correctly parsed
816 [SEC] enh P4 Andr jackx.w.lix@intel.com RESO FIXE New - Rapid RIL 5.4 integration
556 [SEC] enh P4 Andr hellenx.zeng@intel.com VERI FIXE Proximity sensors are not responding.
1356 [SEC] enh P4 Andr norvin.shuster@intel.com ASSI Rebase tool to Download DLL 4.77
1348 enh P4 Andr jianchunx.shen@intel.com ASSI stereo record from mone device: only one channel contains audio
516 [SEC] enh P4 Andr jianjun.liu@intel.com ASSI fail to charge when the battery is dead
814 [SEC] enh P4 Andr honorex.tricot@intel.com ASSI [NLCP] Add NVS auto generation at boot
1257 [SEC] enh P4 Andr wei.gao@borqs.com REOP the camera window size is smaller when phone wake up from idle status
780 [SEC] enh P4 Andr janex.han@intel.com RESO INVA [Audio] Midi file with Kar container cannot be found in audio playlist
1292 [SEC] enh P4 Andr leo.yan@intel.com INTE FIXE sensor_t 's struct member power's value is not set properly
637 [SEC] enh P4 Andr juliex.regairaz@intel.com RESO FIXE start calibrate_wlan script during the first platform boot
444 [SEC] enh P4 Andr alexandre.lewicki@intel.com REOP CWS: Cannot configure browser settings for proxy server to connect to internet
819 [SEC] enh P4 Andr juliex.regairaz@intel.com RESO FIXE CWS-WLAN: Roaming not integrated
1310 [SEC] enh P4 Andr liang.l.yang@intel.com RESO FIXE need add 480p and QVGA video recording resolution
760 [SEC] enh P4 Andr fabienx.marotte@intel.com ASSI [NLCP] Switch TI WiFi driver to NLCP version
1270 [SEC] enh P4 Andr hong.liu@intel.com NEW auto brightness adjust for LCD is not working
384 enh P4 Andr livingston.tong@intel.com RESO FIXE Can't make vocie call
438 [SEC] enh P4 Andr denis.delaveau@intel.com RESO WONT Modem high power consumption in PCH RRC state (Data call)
1008 enh P4 Andr nicholas.j.yoke@intel.com ASSI Feature Request to turn off all IPs by default on a power reset
527 [SEC] enh P4 Andr nicolas.petit@intel.com RESO FIXE Can not control audio from Bluetooth headset
728 [SEC] enh P4 Andr ramesh.babu@intel.com RESO FIXE Mono to stereo sample conversion support in audio drivers/fw.